## Sheet1
Threat | Issue Type | Description | Likelihood | Impact | Responsibility | Current Mitigation | Proposed Mitigation | Response
SQL Database Inaccessible | Technical | MySQL database hosted by the Google Cloud Platform (GCP) could become inaccessible rendering the application unusable | Low | Low | AWS | ensure that sensitive information is stored in environment variables | ensure that sensitive information is stored in environment variables | ensure that sensitive information is stored in environment variables
VM hosting Inaccessible | Technical | The application database relies on the Virtual Machine (VM) which is hosted by the GCP | Low | Low | AWS | N/A | Set back up; dedicated VM; cloning of database | manual restart; failure leads to contacting GCP
COVID - 19 / illness | Non-technical | The virus is still prevalent, despite lockdown measures. It would be very possible to contract the virus or some other disease that would render me unable to complete the project | Low | High | Rohan Chauhan | Following government advice such as the use of face covering and social distancing when in contact with people | Following government directives
Ensuring that passwords are not leaked onto github | Technical | If sensitive information is put on the github unencrypted then the whole repo will be compromised | Low | High | Rohan Chauhan | Using enviroment variable to ensure sensitive information that is crucial to the working of the application is encrypted | same as current mitigation | change senstive information and encrypt
Jenkins sensitive information exposed | Technical | Everytime a new instance of Jenkins is installed and configured by Ansible it would need user settings |  | Low | Rohan Chauhan | Need to store sensitive information for jenkins as local variables | Need to store sensitive information for jenkins as local variables | Need to store sensitive information for jenkins as local variables